## Read Me & Assumptions
FLOW ¦ Phase 4 Financial Decision Model
Seven-tab workbook • Synthetic data • INR • Historical period: Oct 2025–Sep 2026
Model control | Value | Status / source
Project | Customer Onboarding Throughput Transformation | Northstar Cloud Services is fictional
Data classification | Synthetic | No real customer or employer data
Historical period | Oct 2025 – Sep 2026 | 12 months
Management completion target | 240 | Decision target; not historical result
SLA | 35 | Calendar days; defined in KPI_definitions.md
Capacity-hours rule | monthly_capacity_hours is already FTE-adjusted | Do not multiply by FTE_fraction again
Historical average completions / month | 180.6 | Calculated from 12 monthly SQL rows
Historical average receipts / month | 209 | Calculated from 12 monthly SQL rows
Mean calendar cycle time (days) | 40.8 | Phase 3 overall summary
Median calendar cycle time (days) | 35.1 | Phase 3 overall summary
P90 calendar cycle time (days) | 70 | Phase 3 overall summary
SLA attainment | 0.492 | Phase 3 overall summary
Application rework rate | 0.199 | 530 / 2,665 eligible applications
Qualifying rework events (recomputed) | 571 | Raw rework_events joined to applications; positive minutes; non-Invalid status
Qualifying rework minutes (recomputed) | 29814 | Same event rule as above; see Cost Build
Owner monthly capacity hours (sum) | 3631 | 31 owner records; capacity already FTE-adjusted
Weighted owner hourly cost | 682.6577 | Weighted by monthly capacity hours; proxy for cost estimation
Leading bottleneck | Finance Approval | Composite bottleneck evidence ranking
EDITABLE SCENARIO ASSUMPTIONS — provisional, not observed results
Assumption | Conservative | Base | Optimistic | Rationale / caveat
Monthly demand growth | 3% | 2% | 1% | Planning assumption; validate against business outlook
Redesign throughput uplift | 3% | 10% | 18% | Proxy uplift to historical completions, not measured effect
Redesign rework reduction | 5% | 15% | 25% | Applied to qualifying rework labour cost only
Added FTE count | 3 | 2 | 1 | Scenario assumption; does not establish actual staffing need
Monthly cost per added FTE (INR) | 120000 | 100000 | 85000 | Illustrative loaded monthly cost; replace with evidence
One-time redesign implementation cost (INR) | 500000 | 350000 | 250000 | Illustrative estimate
One-time hiring/setup cost per FTE (INR) | 50000 | 40000 | 30000 | Illustrative estimate per added FTE
Added monthly capacity hours per FTE | 95 | 95 | 95 | Illustrative standard capacity assumption
Ramp-up months | 4 | 3 | 2 | Time before full modelled benefits
Other recurring redesign cost / month (INR) | 30000 | 20000 | 15000 | Illustrative support/tool/process cost
Additional throughput per added FTE / month | 8 | 12 | 16 | Explicit productivity proxy; validate with capacity/workload evidence
Rework event active labour cost rate (INR/hour) | 682.6577 | 682.6577 | 682.6577 | Owner hourly rate proxy; rework minutes are estimates
MODEL LIMITATION: Actual active labour hours are not directly measured by task timestamps. Capacity and intervention results are planning estimates. Released capacity is not cash savings. Do not claim modelled benefits as realised.

## Monthly Demand
Monthly Demand & Backlog
Historical monthly flow imported from Phase 3 SQL export; forecast is separate and assumption-driven
Month | Opening backlog | Received | Completed | Cancelled | Calculated closing backlog | SQL closing backlog | Variance | Check
2025-10 | 203 | 158 | 136 | 16 | 209 | 209 | 0 | PASS
2025-11 | 209 | 183 | 139 | 11 | 242 | 242 | 0 | PASS
2025-12 | 242 | 179 | 174 | 18 | 229 | 229 | 0 | PASS
2026-01 | 229 | 159 | 152 | 13 | 223 | 223 | 0 | PASS
2026-02 | 223 | 177 | 144 | 11 | 245 | 245 | 0 | PASS
2026-03 | 245 | 258 | 183 | 17 | 303 | 303 | 0 | PASS
2026-04 | 303 | 198 | 205 | 16 | 280 | 280 | 0 | PASS
2026-05 | 280 | 224 | 183 | 20 | 301 | 301 | 0 | PASS
2026-06 | 301 | 222 | 204 | 15 | 304 | 304 | 0 | PASS
2026-07 | 304 | 246 | 226 | 20 | 304 | 304 | 0 | PASS
2026-08 | 304 | 240 | 223 | 12 | 309 | 309 | 0 | PASS
2026-09 | 309 | 264 | 198 | 15 | 360 | 360 | 0 | PASS
12-MONTH FORECAST — base demand case; forecast is illustrative and not historical
Month | Opening backlog | Forecast receipts | Modelled completions | Assumed cancellations | Forecast closing backlog | Target completions | Gap vs target | Forecast check
2026-10 | 360 | 213 | 181 | 15 | 377 | 240 | 59 | PASS
2026-11 | 377 | 217 | 181 | 15 | 398 | 240 | 59 | PASS
2026-12 | 398 | 222 | 181 | 15 | 424 | 240 | 59 | PASS
2027-01 | 424 | 226 | 181 | 15 | 454 | 240 | 59 | PASS
2027-02 | 454 | 231 | 181 | 15 | 489 | 240 | 59 | PASS
2027-03 | 489 | 235 | 181 | 15 | 528 | 240 | 59 | PASS
2027-04 | 528 | 240 | 181 | 15 | 572 | 240 | 59 | PASS
2027-05 | 572 | 245 | 181 | 15 | 621 | 240 | 59 | PASS
2027-06 | 621 | 250 | 181 | 15 | 675 | 240 | 59 | PASS
2027-07 | 675 | 255 | 181 | 15 | 734 | 240 | 59 | PASS
2027-08 | 734 | 260 | 181 | 15 | 798 | 240 | 59 | PASS
2027-09 | 798 | 265 | 181 | 15 | 867 | 240 | 59 | PASS

## Current-State Capacity
Current-State Capacity
Team/month capacity and complexity indicators from Phase 3; complexity points are not active labour hours
Month | Team | Stage episodes entered | Complexity points | Capacity hours | Points / 100 capacity hours | Interpretation
2025-10 | Sales | 167 | 308 | 510 | 6039% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-10 | RevOps | 175 | 330 | 336 | 9821% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-10 | Legal | 159 | 299 | 375 | 7973% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-10 | Implementation | 312 | 575 | 1548 | 3714% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-10 | Finance | 157 | 292 | 247 | 11822% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-10 | Customer Success | 142 | 255 | 360 | 7083% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-11 | Sales | 201 | 392 | 510 | 7686% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-11 | RevOps | 212 | 409 | 336 | 12173% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-11 | Legal | 192 | 369 | 375 | 9840% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-11 | Implementation | 295 | 539 | 1548 | 3482% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-11 | Finance | 158 | 287 | 247 | 11619% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-11 | Customer Success | 138 | 249 | 360 | 6917% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-12 | Sales | 194 | 343 | 510 | 6725% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-12 | RevOps | 197 | 350 | 336 | 10417% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-12 | Legal | 178 | 316 | 375 | 8427% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-12 | Implementation | 387 | 710 | 1548 | 4587% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-12 | Finance | 210 | 386 | 247 | 15628% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2025-12 | Customer Success | 175 | 319 | 360 | 8861% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-01 | Sales | 173 | 328 | 551 | 5953% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-01 | RevOps | 182 | 341 | 336 | 10149% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-01 | Legal | 150 | 276 | 375 | 7360% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-01 | Implementation | 318 | 572 | 1548 | 3695% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-01 | Finance | 155 | 284 | 247 | 11498% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-01 | Customer Success | 152 | 278 | 360 | 7722% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-02 | Sales | 200 | 357 | 585 | 6103% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-02 | RevOps | 209 | 369 | 336 | 10982% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-02 | Legal | 193 | 348 | 375 | 9280% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-02 | Implementation | 301 | 526 | 1728 | 3044% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-02 | Finance | 176 | 310 | 247 | 12551% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-02 | Customer Success | 151 | 274 | 360 | 7611% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-03 | Sales | 281 | 516 | 585 | 8821% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-03 | RevOps | 271 | 494 | 336 | 14702% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-03 | Legal | 241 | 434 | 375 | 11573% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-03 | Implementation | 410 | 709 | 1728 | 4103% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-03 | Finance | 218 | 380 | 247 | 15385% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-03 | Customer Success | 180 | 309 | 360 | 8583% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-04 | Sales | 222 | 417 | 585 | 7128% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-04 | RevOps | 263 | 505 | 336 | 15030% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-04 | Legal | 222 | 418 | 375 | 11147% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-04 | Implementation | 408 | 753 | 1728 | 4358% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-04 | Finance | 222 | 417 | 247 | 16883% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-04 | Customer Success | 204 | 355 | 360 | 9861% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-05 | Sales | 251 | 469 | 585 | 8017% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-05 | RevOps | 250 | 457 | 336 | 13601% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-05 | Legal | 211 | 383 | 375 | 10213% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-05 | Implementation | 406 | 745 | 1728 | 4311% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-05 | Finance | 195 | 347 | 247 | 14049% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-05 | Customer Success | 190 | 354 | 360 | 9833% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-06 | Sales | 251 | 458 | 585 | 7829% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-06 | RevOps | 271 | 500 | 336 | 14881% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-06 | Legal | 237 | 438 | 375 | 11680% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-06 | Implementation | 417 | 751 | 1728 | 4346% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-06 | Finance | 245 | 453 | 247 | 18340% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-06 | Customer Success | 202 | 361 | 360 | 10028% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-07 | Sales | 266 | 484 | 585 | 8274% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-07 | RevOps | 269 | 487 | 336 | 14494% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-07 | Legal | 242 | 437 | 375 | 11653% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-07 | Implementation | 469 | 842 | 1728 | 4873% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-07 | Finance | 234 | 428 | 247 | 17328% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-07 | Customer Success | 222 | 387 | 360 | 10750% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-08 | Sales | 260 | 468 | 585 | 8000% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-08 | RevOps | 264 | 477 | 336 | 14196% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-08 | Legal | 237 | 424 | 375 | 11307% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-08 | Implementation | 451 | 824 | 1728 | 4769% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-08 | Finance | 237 | 424 | 247 | 17166% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-08 | Customer Success | 224 | 411 | 360 | 11417% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-09 | Sales | 297 | 544 | 585 | 9299% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-09 | RevOps | 304 | 566 | 336 | 16845% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-09 | Legal | 266 | 502 | 375 | 13387% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-09 | Implementation | 424 | 770 | 1548 | 4974% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-09 | Finance | 241 | 445 | 247 | 18016% | Workload intensity proxy; not a direct utilisation or active-hours measure.
2026-09 | Customer Success | 201 | 370 | 360 | 10278% | Workload intensity proxy; not a direct utilisation or active-hours measure.
Owner-level detail (raw owner table + Phase 3 workload measures)
Owner ID | Team | FTE fraction | Monthly capacity hours (already FTE-adjusted) | Cost per hour (INR) |  | Complexity points / capacity hour
S01 | Sales | 1 | 75 | 710 |  | 0.571
S02 | Sales | 1 | 75 | 770 |  | 0.535
S03 | Sales | 1 | 75 | 790 |  | 0.634
S04 | Sales | 1 | 75 | 700 |  | 0.631
S05 | Sales | 1 | 75 | 660 |  | 0.821
S06 | Sales | 0.8 | 60 | 680 |  | 0.913
S07 | Sales | 1 | 75 | 800 |  | 0.9
S08 | Sales | 1 | 75 | 760 |  | 1.114
R01 | RevOps | 0.8 | 96 | 570 |  | 1.275
R02 | RevOps | 1 | 120 | 620 |  | 1.251
R03 | RevOps | 1 | 120 | 540 |  | 1.374
L01 | Legal | 1 | 150 | 1030 |  | 0.962
L02 | Legal | 1 | 150 | 1020 |  | 1.03
L03 | Legal | 0.5 | 75 | 1080 |  | 1.142
F01 | Finance | 1 | 95 | 690 |  | 1.432
F02 | Finance | 1 | 95 | 770 |  | 1.447
F03 | Finance | 0.6 | 57 | 620 |  | 1.523
I01 | Implementation | 1 | 180 | 660 |  | 0.366
I02 | Implementation | 1 | 180 | 690 |  | 0.366
I03 | Implementation | 1 | 180 | 670 |  | 0.409
I04 | Implementation | 1 | 180 | 650 |  | 0.371
I05 | Implementation | 1 | 180 | 590 |  | 0.423
I06 | Implementation | 1 | 180 | 660 |  | 0.444
I07 | Implementation | 1 | 180 | 610 |  | 0.427
I08 | Implementation | 1 | 180 | 630 |  | 0.466
I09 | Implementation | 1 | 180 | 580 |  | 0.481
I10 | Implementation | 0.6 | 108 | 590 |  | 0.46
C01 | Customer Success | 1 | 90 | 550 |  | 0.777
C02 | Customer Success | 1 | 90 | 590 |  | 0.802
C03 | Customer Success | 1 | 90 | 530 |  | 0.912
C04 | Customer Success | 1 | 90 | 500 |  | 1.121
Interpretation
The provided team dataset measures complexity points per capacity hour. It does not establish active labour hours or a direct throughput-per-hour relationship. Scenario throughput uplifts are therefore explicit planning assumptions, not a causal finding.

## Cost Build
Cost Build
Source-supported rework estimate and transparent placeholders; do not interpret elapsed time as active labour
Cost component | Value | Unit | Source / formula | Evidence status
Completed applications | 2167 | applications | Phase 3 scalar validation | Observed synthetic-data count
Qualifying rework events | 571 | events | Raw events linked to application; positive minutes; status not Invalid | Recomputed from raw data
Qualifying estimated rework minutes | 29814 | minutes | Same qualifying-event rule | Estimated effort input
Qualifying estimated rework hours | 496.9 | hours | Minutes / 60 | Derived estimate
Capacity-weighted owner cost rate | 682.6577 | INR/hour | Owner monthly capacity-weighted cost per hour | Proxy
Estimated rework labour cost | 339212.5963 | INR | Estimated rework hours × weighted cost rate | Modelled estimate
Estimated rework cost per completed application | 156.5356 | INR/application | Estimated rework labour cost / completed applications | Modelled estimate
Other direct cost per completion | 8000 | INR/application | Provisional placeholder from initial planning hypothesis; not validated as actual | Assumption — replace
Illustrative total cost per completion | 8156.5356 | INR/application | Rework estimate + provisional other cost; incomplete cost build | Illustrative only
Illustrative monthly cost at target | 1957568.5386 | INR/month | Illustrative unit cost × 240 target | Illustrative only
Annual qualifying rework labour cost | 339212.5963 | INR/year | Estimated qualifying rework labour cost across the 12-month historical period; not annualised again | Historical-period estimate; not a forward annual forecast
Cost interpretation and limitations
• Task elapsed time is not a direct measure of hands-on labour; no task-duration cost is claimed as measured.
• Rework estimated_minutes is itself an estimate. Cost uses a capacity-weighted owner hourly rate as a proxy, not a verified owner-to-event rate.
• ₹8,000 per completion is a provisional planning hypothesis and must not be described as a validated historical cost.
• Released capacity is not cash savings. Cashable savings require a defensible reduction in actual cash expenditure.
• Do not add rework cost reduction, capacity release and incremental throughput as independent financial benefits without proving no overlap.

## Intervention Scenarios
Intervention Scenarios
A–D comparison across conservative/base/optimistic cases; capacity effect is an explicit throughput proxy
Option | Scenario | Demand / month | Baseline throughput proxy | Redesign uplift | Added FTE | Added throughput / FTE | Modelled throughput | Gap to demand | One-time redesign cost | One-time hiring cost | Annual recurring cost | First-year modelled cost | Gap to 240 target | Estimated rework cost reduction proxy (INR/year) | Ramp-up-adjusted recurring cost (INR) | Net modelled first-year impact (INR; proxy only) | Recurring annual cost after ramp-up (INR) | Uncapped modelled capacity
A — No change | Conservative | 215.27 | 180.5833 | 0% | 0 | 0 | 180.5833 | 34.6867 | 0 | 0 | 0 | 0 | 59.4167 | 0 | 0 | 0 | 0 | 180.5833
A — No change | Base | 213.18 | 180.5833 | 0% | 0 | 0 | 180.5833 | 32.5967 | 0 | 0 | 0 | 0 | 59.4167 | 0 | 0 | 0 | 0 | 180.5833
A — No change | Optimistic | 211.09 | 180.5833 | 0% | 0 | 0 | 180.5833 | 30.5067 | 0 | 0 | 0 | 0 | 59.4167 | 0 | 0 | 0 | 0 | 180.5833
B — Process redesign | Conservative | 215.27 | 180.5833 | 3% | 0 | 0 | 186.0008 | 29.2692 | 500000 | 0 | 360000 | 860000 | 53.9992 | 11307.0865 | 240000 | -848692.9135 | 360000 | 186.0008
B — Process redesign | Base | 213.18 | 180.5833 | 10% | 0 | 0 | 198.6417 | 14.5383 | 350000 | 0 | 240000 | 590000 | 41.3583 | 38161.4171 | 180000 | -551838.5829 | 240000 | 198.6417
B — Process redesign | Optimistic | 211.09 | 180.5833 | 18% | 0 | 0 | 211.09 | 0 | 250000 | 0 | 180000 | 430000 | 26.9117 | 70669.2909 | 150000 | -359330.7091 | 180000 | 213.0883
C — Additional staffing | Conservative | 215.27 | 180.5833 | 0% | 3 | 8 | 204.5833 | 10.6867 | 0 | 150000 | 4320000 | 4470000 | 35.4167 | 0 | 2880000 | -4470000 | 4320000 | 204.5833
C — Additional staffing | Base | 213.18 | 180.5833 | 0% | 2 | 12 | 204.5833 | 8.5967 | 0 | 80000 | 2400000 | 2480000 | 35.4167 | 0 | 1800000 | -2480000 | 2400000 | 204.5833
C — Additional staffing | Optimistic | 211.09 | 180.5833 | 0% | 1 | 16 | 196.5833 | 14.5067 | 0 | 30000 | 1020000 | 1050000 | 43.4167 | 0 | 850000 | -1050000 | 1020000 | 196.5833
D — Redesign + targeted staffing | Conservative | 215.27 | 180.5833 | 3% | 3 | 8 | 210.0008 | 5.2692 | 500000 | 150000 | 4680000 | 5330000 | 29.9992 | 11307.0865 | 3120000 | -5318692.9135 | 4680000 | 210.0008
D — Redesign + targeted staffing | Base | 213.18 | 180.5833 | 10% | 2 | 12 | 213.18 | 0 | 350000 | 80000 | 2640000 | 3070000 | 17.3583 | 38161.4171 | 1980000 | -3031838.5829 | 2640000 | 222.6417
D — Redesign + targeted staffing | Optimistic | 211.09 | 180.5833 | 18% | 1 | 16 | 211.09 | 0 | 250000 | 30000 | 1200000 | 1480000 | 10.9117 | 70669.2909 | 1000000 | -1409330.7091 | 1200000 | 229.0883
Important
Baseline throughput is average historical completions, not a proven theoretical capacity. Added throughput per FTE and redesign uplifts are provisional assumptions. Modelled throughput is capped at demand. Costs are not netted against benefits because validated cashable savings are not yet established.

## Sensitivity Analysis
Sensitivity Analysis
Editable ranges and linked model outputs; review scenario ranking under assumption changes
Driver | Low | Base | High | Affected outcome | Linked assumption | Interpretation | Status | Low-case uncapped capacity | Base-case uncapped capacity | High-case uncapped capacity | Low-case gap to 240 | Base-case gap to 240 | High-case gap to 240 | Low-case cost / benefit proxy (INR) | Base-case cost / benefit proxy (INR) | High-case cost / benefit proxy (INR)
Monthly demand growth | 1% | 2% | 3% | Demand and capacity gap | Read Me & Assumptions row 27 | Higher demand may increase backlog even if throughput improves | Modelled; validate assumptions | 222.6417 | 222.6417 | 222.6417 | 17.3583 | 17.3583 | 17.3583
Redesign throughput uplift | 3% | 10% | 18% | Modelled throughput | Read Me & Assumptions row 28 | Assumption needs evidence from a pilot or comparable operation | Modelled; validate assumptions | 210.0008 | 222.6417 | 237.0883 | 29.9992 | 17.3583 | 2.9117
Rework reduction | 5% | 15% | 25% | Rework cost estimate | Read Me & Assumptions row 29 | Cost sensitivity only; not assumed to create cash savings automatically | Modelled; validate assumptions | 222.6417 | 222.6417 | 222.6417 | 17.3583 | 17.3583 | 17.3583 | 16960.6298 | 50881.8894 | 84803.1491
Monthly cost per added FTE | 85000 | 100000 | 120000 | Annual recurring staffing cost | Read Me & Assumptions row 31 | Higher cost weakens staffing economics | Modelled; validate assumptions | 222.6417 | 222.6417 | 222.6417 | 17.3583 | 17.3583 | 17.3583 | 2040000 | 2400000 | 2880000
One-time redesign cost | 250000 | 350000 | 500000 | First-year cost | Read Me & Assumptions row 32 | Estimate requires implementation scope | Modelled; validate assumptions | 222.6417 | 222.6417 | 222.6417 | 17.3583 | 17.3583 | 17.3583 | 490000 | 590000 | 740000
Added throughput per FTE | 8 | 12 | 16 | Modelled throughput | Read Me & Assumptions row 37 | Must be validated against operational capacity evidence | Modelled; validate assumptions | 214.6417 | 222.6417 | 230.6417 | 25.3583 | 17.3583 | 9.3583
Sensitivity interpretation
Throughput columns show uncapped modelled capacity so the 240 target gap remains visible. Demand-capped throughput is retained in Intervention Scenarios column H; demand gap remains column I. Low/base/high values are stress tests, not confidence intervals. Rework cost reductions are effort-cost proxies, not proven cash savings.

## Recommendation
Recommendation & Decision Gate
Decision support only: preferred option must follow validated model outputs and justified assumptions
Management question | Which intervention most defensibly closes the monthly demand gap without unacceptable cost or risk?
Option | Base-case demand | Base-case throughput | Gap to demand | First-year modelled cost | Key trade-off | Assessment | Gap to 240 target | Recurring annual cost | Net first-year impact (proxy only)
A — No change | 213.18 | 180.5833 | 32.5967 | 0 | No implementation cost; backlog risk may persist | 240 target gap remains | 59.4167 | 0 | 0
B — Process redesign | 213.18 | 198.6417 | 14.5383 | 590000 | May improve throughput and reduce rework; uplift unverified | 240 target gap remains | 41.3583 | 240000 | -551838.5829
C — Additional staffing | 213.18 | 204.5833 | 8.5967 | 2480000 | Adds recurring cost; actual staffing need unverified | 240 target gap remains | 35.4167 | 2400000 | -2480000
D — Redesign + targeted staffing | 213.18 | 213.18 | 0 | 3070000 | Potential combined benefit; interaction and costs require validation | 240 target gap remains | 17.3583 | 2640000 | -3031838.5829
Recommendation status
CONDITIONAL — No option should be declared a winner from synthetic assumptions alone. Compare the base-case gap to 240, first-year and recurring costs, and the rework-cost reduction proxy. If no option closes the target gap, pilot the lowest-risk feasible option and validate throughput, staffing and cashable benefits before approval.
Decision criteria
1. Meet demand sustainably, not just in a single month.
2. Compare first-year costs separately from recurring annual costs.
3. Do not treat released staff time as cash savings without evidence of cash expenditure reduction.
4. Check the effect of demand growth, intervention effectiveness, staffing cost and implementation cost.
5. If no option closes the gap, report the residual gap and the next evidence or intervention required.